# Project Status Update: Roof Ventilation & Insulation Retrofit

Date: January 11, 2026 Property: 1517 San Juan Ave

Status: CRITICAL PAUSE (Insulation Work Suspended)

## 1. Executive Summary

The insulation retrofit (Advance Insulation) is officially paused. New "thermal tracking" (ghosting) and mold in a second bedroom confirm active air leakage from the interior to the attic.

Forensic calculation identifies the root cause as a severe Ventilation Imbalance from the 2024 roof replacement. The attic is depressurized, acting as a vacuum on the living space.

## 2. The Technical Failure (The Math)

- Exhaust Capacity (Ridge): 60 ft Omni Vent × 18 NFA/ft = 1,080 sq. in.

- Intake Capacity (Eave): 12 SV-50 Vents × 50 NFA/unit = 600 sq. in. (Theoretical Max)

- The Deficit: -480 sq. in. (Minimum)

- Result: The ridge vent is starving for air, creating negative pressure that pulls warm, moist air through the ceiling plane.

## 3. Recent Developments (Jan 10-11, 2026)

### A. The Insulation Pause

- Action: Notified Brodie (Advance Insulation) to hold scheduling.

- Reason: Confirmed that insulating before fixing the intake would trap moisture and fail to stop the vacuum effect.

### B. The Text Exchange with Vintage Roofing (Mark)

- User Action: Informed Mark of the calculation (1080 vs 600) and the plan to hire independent inspectors.

- Mark’s Admission: “If these soffits were to get converted / vented. Those low air vents would alter the air flow by exhaust instead of drawing air.”

- Strategic Win: Mark explicitly admitted that his vents (SV-50) are incompatible with proper soffit ventilation. This confirms they must be removed if soffits are upgraded.

## 4. The Action Plan (The "Split Solution")

The remediation strategy separates the "Correction" from the "Upgrade" to minimize conflict and ensure quality.

### Phase 1: Verification (Current Stage)

- Objective: Obtain a written/verbal "Failure Diagnosis" from a neutral 3rd party.

- Target Companies: Parker Johnston, Proline, or CSC (for inspection/report only).

- Key Question: "Can these 12 SV-50s mathematically support a 60-foot Omni Ridge Vent?"

- Status: Scheduling in progress.

### Phase 2: The Demand (Warranty Claim)

- Trigger: Immediately following the independent inspection.

- The Offer to Mark:

  - Mark (Vintage): Removes 12 SV-50 vents and patches the roof deck (Warranty Work).

  - User (You): Hires a specialist to cut continuous soffit vents (The Upgrade).

### Phase 3: Execution

- Step 1 (The Upgrade): Irwin Industries (or similar Building Envelope Specialist) cuts 3" continuous strip vent in stucco (~1,080+ sq. in. intake).

- Step 2 (The Repair): Vintage Roofing patches the 12 roof deck holes.

- Step 3 (The Restoration): Advance Insulation performs mold remediation, air sealing, and insulation install once attic pressure is neutral.

## 5. Outstanding Questions / Risks

- Mark's Resistance: Will he try to argue the vacuum effect isn't his fault?

  - Counter: The math (1080 vs 600) and Manufacturer Manual ("Not for Intake") override his opinion.

- Inspection Timing: Need to secure an inspection date ASAP to prevent long delays.